LOOKAHEAD-DRIVEN

ASSET PLANNING

Implementation Guide for Dev Team

AI-Assisted MVP — Mapped to Sitespace API

ARC Bowden Apartments — March 2026

Green = already built. Amber = extend existing. Blue = net new. Red = codebase caveat.

# 1. What Are We Building?

A new feature on top of Sitespace that reads a construction programme, uses AI to understand its structure and classify asset needs, then feeds demand data into your existing booking and notification systems.

Most infrastructure already exists. Subcontractor management, booking with conflict checking, asset availability, audit trail, email integration — all built. This feature adds a programme → activities → asset demand pipeline that plugs into what you’ve got.

One-line summary Programme goes in → AI reads and classifies it → demand forecast comes out → existing booking system handles the rest.

# 2. What You Already Have

Existing Sitespace infrastructure this feature reuses:

Subcontractor management — fully built Sub accounts, trade_specialty column (String, not a formal enum), project assignment (subcontractor_site_project), availability checking, welcome email invite, search by trade, activate/deactivate.

Booking + conflict checking — fully built POST /api/bookings with auto-confirm for managers / pending for subs, /check-conflicts, /check-availability, bulk booking, calendar view (90 days), statistics, duplicate endpoint.

Audit trail — fully built booking_audit_logs table, immutable. Per-booking, user activity, project-level. Deterministic paper trail for construction disputes.

Email — fully built Mailtrap in app/core/email.py. Welcome, password reset, verification templates. New notification templates use the same service.

Auth + RBAC — fully built JWT HS512, roles (admin/manager/subcontractor/tv), project-scoped permissions, rate limiting via slowapi. Note: subcontractor auth is a separate flow from user auth — GET /api/auth/me/subcontractor exists. New sub-facing endpoints must use get_current_subcontractor dependency.

File upload — two active routes Legacy POST /api/uploadfile/ (active, supports CSV/XLSX). New POST /api/files/upload (active, images + PDF only, used by site plans). Neither is suitable for programme upload. Programme upload uses a new dedicated route at POST /api/programmes/upload per build rule #4 — do not reuse or modify existing upload routes.

File storage abstraction — available stored_files table + app/utils/storage.py (local today, S3-ready). Consider using file_id (FK → stored_files) on programme_uploads instead of raw file_path for consistency with how site plans work.

# 3. Net New vs Extend — Full Audit

| Stream | Status | Work Required |
| --- | --- | --- |
| 1. Ingestion | Net New | New /api/programmes/ routes, AI service, programme_uploads + programme_activities tables |
| 2. Asset Mapping | Net New | New activity_asset_mappings table, AI classifier, review UI. Links to existing assets table |
| 3. Scope Assign | Already Built | Wire programme_activities to existing subcontractor_site_project. Add activity-level filtering |
| 4. Lookahead | Net New | New service joining programme_activities + activity_asset_mappings + slot_bookings. Caveat: slot_bookings stores Date + Time separately — reconstruct duration carefully |
| 5. Notifications | Extend | New job + templates. Uses existing Mailtrap. APScheduler is genuinely new infra (no existing scheduler). Add notifications table |
| 6. Deep Link | Extend | Add query params to existing POST /api/bookings. One nullable column on slot_bookings |
| 7. Frontend | Net New | PM dashboard (upload, mapping, heatmap). Sub view (activities, alerts, book-now) |

Summary Of 7 streams: 1 already built, 2 minor extensions, 4 net new. New work = data pipeline (ingestion → mapping → lookahead) + frontend.

# 4. What the Real Programme Looks Like

Validated against ARC Bowden Apartments v36.1 — 28-page P6 programme from Hindmarsh.

## Structure

Tree: Project → Phase → Level → Zone → Activities. Hierarchy via naming/indentation/WBS codes. AI detects it.

Known crane keywords Lift column cages ¦ Jump the Hoist ¦ Lift BD falsework ¦ Install precast wall panels ¦ Lift BD reo ¦ Lift screw-in bars

## Floor cycle overlaps

Every level: survey → columns → precast → BD falsework → scaffold → reo → pour. 2–3 levels overlap = concurrent crane demand.

## Zone splits

Lower levels split Zone A/B sequentially. Crane in bursts per zone. Map at activity level.

# 5. Build Order

⚡ = AI component. ✅ = reuses existing Sitespace code.

## ⚡ Stream 1: Programme Ingestion (AI-Driven)

Accept uploads, AI detects structure. Entirely net new.

### New DB models (Alembic)

- programme_uploads: id (UUID), project_id (FK → site_projects), uploaded_by (FK → users), file_name, file_id (FK → stored_files, uses existing storage abstraction), column_mapping (JSONB — use sqlalchemy.dialects.postgresql.JSONB, not generic JSON), version_number, created_at. Immutable.

- programme_activities: id (UUID), programme_upload_id (FK), parent_id (self-ref), name, start_date, end_date, duration_days, level_name, zone_name, is_summary, wbs_code, sort_order.

JSONB dialect column_mapping uses JSONB (from sqlalchemy.dialects.postgresql import JSONB). Existing models use generic JSON (e.g. booking_audit_logs.changes). JSONB is correct for new tables — supports indexing and querying. Be explicit in the model definition.

### New routes: /api/programmes/

| Method | Path | Description |
| --- | --- | --- |
| POST | /api/programmes/upload | Upload CSV/XLSX, trigger AI |
| GET | /api/programmes/{project_id} | List versions for project |
| GET | /api/programmes/{upload_id}/activities | Activity tree for version |
| PUT | /api/programmes/{upload_id}/confirm | PM confirms AI mapping |
| GET | /api/programmes/{upload_id}/diff | Diff vs previous version |

Auth: manager/admin. Project-scoped via existing membership check.

### New service: app/services/ai_service.py

- Two methods: detect_structure(rows) and classify_assets(activities).

- API key from AI_API_KEY env var. All calls through backend.

- Timeouts: 8s structure, 3s classification. httpx async.

- Validate JSON schema. Invalid = raise exception, handler falls back.

### AI structure call

Input: First 50–100 rows as JSON (via openpyxl/csv). Include headers.

Prompt: System msg explains P6/MS Project. Return column_mapping + activities tree.

Model: Claude Haiku or GPT-4o-mini. Simple classification.

Cost: $0.01–0.05 per upload.

Large files: AI analyses first 50–100 rows. Apply schema deterministically to rest.

Example system prompt You are a construction scheduling expert. Given programme export rows: (1) Map headers to activity_name, start_date, finish_date, duration, activity_id, wbs_level, percent_complete, or unknown. (2) Parse into hierarchical tree with summary rows as parents. Return ONLY JSON: {column_mapping: {...}, activities: [{id, name, start, finish, parent_id, is_summary, level_name, zone_name}]}.

- Caching: SHA-256 header hash. Same hash = skip AI, reuse mapping.

- Re-upload: Match by name + level. Carry forward mappings. Flag >3 day shifts.

- Fallback: AI fails = empty dropdowns + flat list. PM maps manually.

Done when Upload Bowden CSV → tree in <8s → PM confirms → correct levels/zones. Different columns → AI maps. Re-upload → mappings carry forward.

## ⚡ Stream 2: Asset Mapping + AI Classifier

AI classifies activities by asset type. PM bulk-confirms.

### New DB model

- activity_asset_mappings: id (UUID), programme_activity_id (FK), asset_type (crane/hoist/loading_bay), confidence (high/med/low), suggested_by (keyword/ai/manual), is_confirmed, confirmed_by (FK → users), confirmed_at, subcontractor_id (FK → subcontractors, nullable).

Codebase caveat: assets.type is free-text activity_asset_mappings.asset_type values (crane, hoist, loading_bay) must match whatever strings are stored in assets.type in production. There is no enum enforcing this. Onboarding must establish consistent asset type naming, or lookahead matching will silently fail. Add a validation check or admin config for allowed asset type values.

### New routes

| Method | Path | Description |
| --- | --- | --- |
| POST | /.../mappings/classify | Trigger AI classification |
| GET | /.../mappings | All mappings + confidence |
| POST | /.../mappings/bulk-confirm | Confirm all high-confidence |
| PUT | /.../mappings/{id} | Edit single mapping |

Batching: 100 activities/call. Parallel for 500+. ~$0.003/batch.

- High: AI + keyword agree. Auto-selected.

- Medium: AI confident, no keyword. PM confirms.

- Low: AI unsure in structural phase. Amber flag.

- Learning: Store corrections. After 50+ per builder, inject as few-shot.

Done when ~80% correct first pass → bulk-confirm → review 10–20 flagged → under 5 mins for 200+ activities.

## ✅ Stream 3: Subcontractor Scope Assignment

Mostly built. Existing sub management covers it.

### Already exists

- subcontractor_site_project join table

- POST /{project_id}/subcontractors

- GET /{project_id}/available-subcontractors

- POST /{sub_id}/send-welcome-email

- trade_specialty column (String(100), not a formal enum), availability checking

### Add (~1–2 days)

- subcontractor_id on activity_asset_mappings links activities to subs.

- GET /api/programmes/{upload_id}/activities?subcontractor_id={sub_id}.

Minimal new code Wire programme_activities to existing sub-project relationships. No new auth or invite flow.

## Stream 4: Lookahead Engine (Deterministic)

Core new logic. Joins programme data against existing bookings. No AI.

Codebase caveat: slot_bookings stores Date + Time separately slot_bookings has booking_date (Date) + start_time (Time) + end_time (Time) — not a DateTime range. Compute booked_hours = SUM(end_time - start_time) grouped by (asset_id, week). Do not assume DateTime ranges in queries.

### app/services/lookahead_engine.py

Joins three sources:

- programme_activities: Confirmed activities with dates.

- activity_asset_mappings: Which activities need which asset types.

- slot_bookings: Your existing table. Reconstruct duration from (end_time - start_time) per booking_date. Aggregate per week per asset type.

Output per week: asset_type, demand_hours, booked_hours, demand_level (Low/Med/High/Critical), gap_hours.

- Thresholds: Low <8, Med 8–20, High 20–40, Critical 40+ hrs/wk.

- Booking check: Compare durations. 2hr booking for 3-day activity = gap.

- Asset matching: Join on asset_type string. Verify assets.type values in production match the categories used in activity_asset_mappings (crane/hoist/loading_bay). No enum enforces this — add a validation step.

### New routes: /api/lookahead/

| Method | Path | Description |
| --- | --- | --- |
| GET | /api/lookahead/{project_id} | Demand heatmap data |
| GET | /api/lookahead/{project_id}/alerts | Unbooked demand for notifications |
| GET | /api/lookahead/{project_id}/sub/{sub_id} | Filtered demand for a sub |

Codebase caveat: subcontractor auth GET /api/lookahead/{project_id}/sub/{sub_id} must accept subcontractor JWT tokens. The codebase has separate auth flows — use get_current_subcontractor dependency, not get_current_user. Verify this for every new endpoint subs access.

Auth: manager/admin see all. Subs see own demand via sub auth flow.

Scheduling: Nightly via APScheduler. No existing scheduler infrastructure — APScheduler is genuinely new. Add startup/shutdown lifecycle hooks in app/main.py. Current background tasks use threading.Thread(daemon=True) for emails only.

Done when Heatmap: weeks x assets, colour-coded. Booking overlay shows booked vs needed.

## ✅ Stream 5: Notifications (Extend Existing)

New scheduled job using your existing Mailtrap service.

### Already exists

- Mailtrap in app/core/email.py

- Template-based email sending

### Add (~3–4 days)

- notifications table (id, sub_id, activity_id, asset_type, trigger_type, status, sent_at, acted_at, booking_id).

- 3 email templates: 6-week, 3-week, 1-week. Each with Book Now link.

- Nightly job via APScheduler (new infra — see Stream 4 note): query lookahead for gaps. Send if due + not suppressed.

- Suppression: booking duration ≥ demand = skip.

- GET /api/notifications/my for subs. Use get_current_subcontractor auth dependency.

## ✅ Stream 6: Book Now Deep Link (Extend Existing)

Query params on existing booking creation. ~1 day.

### Already exists

- POST /api/bookings/ with conflict checking

- Auto-CONFIRMED / PENDING by role

### Add

- Frontend form accepts ?asset_type=crane&date_from=...&date_to=...&source=lookahead.

- Nullable source column on slot_bookings.

- On success, update notification status to “acted.”

- Subs booking via deep link: ensure POST /api/bookings/ accepts subcontractor JWT (existing — verify get_current_subcontractor works here).

## Stream 7: Frontend (Net New)

Two views. Build parallel with Streams 5–6.

### PM Dashboard

- Upload: file picker → AI spinner → column mapping confirm → tree preview

- Mapping review: confidence badges, bulk confirm, manual edit

- Heatmap: weeks x assets, colour-coded, booking overlay

- Version history with diff

### Sub View

- Filtered activities (their trade)

- Notification feed + Book Now buttons

- Calendar with upcoming needs

- Tech: Recharts/CSS grid. No Gantt.

- Mobile: Sub view must work on mobile.

- TV role: Existing tv users see heatmap read-only.

# 6. AI Decision Framework

| Use AI | Keep Deterministic |
| --- | --- |
| Column mapping | Demand calculation |
| Hierarchy detection | Booking comparison |
| Asset classification | Change detection |
|  | Notifications |
|  | Conflict surfacing |

AI = classification + human confirm. PM always confirms. Blast radius: 10 extra seconds.

Core logic = auditable. Court-ready deterministic answers.

Conflict resolution = people. System surfaces. Humans resolve.

## Phase 2

- Predictive demand: Needs 6–12 months data.

- NL queries: Not MVP.

- Auto sub-trade match: Too error-prone.

# 7. AI Technical Requirements

## New env vars (add to .env + config.py)

- AI_PROVIDER: anthropic or openai

- AI_API_KEY: Never commit

- AI_MODEL: claude-haiku or gpt-4o-mini

- AI_TIMEOUT_STRUCTURE: 8

- AI_TIMEOUT_CLASSIFY: 3

- AI_RATE_LIMIT: 10 calls/min/user

- AI_ENABLED: true (feature flag)

## New pip deps (add to requirements.txt)

- anthropic or openai: LLM SDK

- openpyxl: Excel reading (not currently installed)

- apscheduler: Nightly job (no existing scheduler infrastructure — add startup/shutdown lifecycle hooks in app/main.py)

## Prompts

- Versioned config (app/services/prompts/). Not hardcoded.

- 3–5 few-shot from Bowden data.

- JSON only. Validate schema. Invalid = fallback.

## Learning loop

- ai_suggestion_logs table (suggestion + PM result).

- Track accuracy per project. Target 85%+ in 3 months.

- After 50+ corrections, inject as few-shot per builder.

No fine-tuning for MVP Few-shot gets 80–90%. Fine-tuning needs thousands of examples. Revisit at 6+ months.

## Fallback matrix

| Failure | Ingestion Fallback | Classifier Fallback |
| --- | --- | --- |
| Timeout | Empty dropdowns + flat list | Keyword-only |
| Bad JSON | Empty dropdowns + flat list | Keyword-only |
| Rate limit | Queue, retry 60s | Queue, retry 60s |
| Key expired | Alert ops, manual | Alert ops, keyword |
| AI_ENABLED=false | Manual mapping | Keyword-only |

Golden rule Feature works with AI_ENABLED=false. AI = accelerator, not dependency.

# 8. Database Migration Summary

## New tables

| Table | Purpose | Key FKs |
| --- | --- | --- |
| programme_uploads | Versioned files | site_projects, users, stored_files |
| programme_activities | Activity tree | programme_uploads, self-ref |
| activity_asset_mappings | AI + PM classifications | programme_activities, users, subs |
| notifications | Alert state machine | subcontractors, programme_activities |
| lookahead_snapshots | Cached demand | site_projects |
| ai_suggestion_logs | AI accuracy tracking | programme_uploads, users |

## Modified tables

| Table | Change |
| --- | --- |
| slot_bookings | Add nullable source column for lookahead-originated bookings |

JSONB note programme_uploads.column_mapping uses JSONB (from sqlalchemy.dialects.postgresql import JSONB). Existing models use generic JSON. JSONB is correct for new tables — supports indexing. Be explicit in model definition.

# 9. Codebase Caveats (From Audit)

These were identified by running the guide against the live codebase. Address during implementation:

| # | Issue | Impact |
| --- | --- | --- |
| 1 | slot_bookings: Date + Time split | Lookahead engine must reconstruct duration from end_time - start_time per day |
| 2 | assets.type is free-text | Asset type matching needs validation. No enum. Onboard with consistent naming |
| 3 | trade_specialty is String(100) | Not an enum. Do not reference TradeSpecialty in code |
| 4 | Sub auth is separate flow | Use get_current_subcontractor for sub-facing endpoints in Streams 4, 5, 6 |
| 5 | No scheduler infrastructure | APScheduler is new. Add lifecycle hooks in app/main.py |
| 6 | JSONB dialect required | Use sqlalchemy.dialects.postgresql.JSONB, not generic JSON |
| 7 | stored_files pattern available | Use file_id FK instead of raw path for programme file storage |
| 8 | File upload not disabled | Two active routes exist. Neither suitable. Use new /api/programmes/upload |

# 10. Build Summary

| Stream | Status | What | Depends On |
| --- | --- | --- | --- |
| ⚡ 1. Ingestion | New | Upload + AI structure | Start here |
| ⚡ 2. Mapping | New | AI classify + confirm | Stream 1 |
| ✅ 3. Scope | Built | Wire to existing subs | Stream 2 |
| 4. Lookahead | New | Demand calc | Streams 2+3 |
| ✅ 5. Notify | Extend | Job + existing email | Stream 4 |
| ✅ 6. Deep Link | Extend | Params on bookings | Stream 4 |
| 7. Frontend | New | PM + sub views | All |

# 11. Rules for the Build

- CSV/Excel only. No PDF.

- AI reads structure. No custom parser.

- UUIDs. Follow Sitespace conventions.

- New routes: /api/programmes/ and /api/lookahead/. Do not reuse existing upload routes. Only modify slot_bookings (source column).

- AI suggests, PM confirms. Never auto-commit.

- Timeout + fallback on every AI call. Works with AI_ENABLED=false.

- Log suggestions + corrections (ai_suggestion_logs).

- Nightly lookahead recalc via APScheduler (new infra).

- Compute booked hours from end_time - start_time per booking_date. Do not assume DateTime ranges.

- Sub-facing endpoints use get_current_subcontractor auth dependency.

- Sub view on mobile. Existing RBAC for all new endpoints.

# 12. Your First Week

- Mon: AI env vars in config.py. pip install openpyxl, apscheduler, anthropic/openai into requirements.txt. Build ai_service.py, test prompt. Alembic migration: programme_uploads (with file_id FK to stored_files, JSONB column_mapping) + programme_activities.

- Tue: POST /api/programmes/upload — openpyxl reader + AI structure call + save. Test with Bowden CSV.

- Wed: Confirmation UI. activity_asset_mappings table + POST classify endpoint. AI classifier + keyword boost.

- Thu: Mapping review UI (badges, bulk confirm). Migration: notifications + lookahead_snapshots + ai_suggestion_logs. Wire APScheduler lifecycle hooks in app/main.py.

- Fri: E2E: upload → AI structures → confirm → AI classifies → bulk-confirm. Verify sub auth works on /api/lookahead sub endpoint. Demo. Start lookahead engine.

Questions? Flag early.